## progress
WORKING PROGRESS
PROJECT DASHBOARD ASTRA VISTEON INDONESIA
WEEK | PLAN | RESULT | NOTES
1 | Create view login page | ✔️ | -
| Create backend login with 2 role | ✔️ | -
| Use 2 role ( Admin & User) | ✔️ | Admin can manage users
| Create view admin page (user list) | ✔️ | -
| Create view user page (profile user) | ✔️ | -
| Create view CRUD user | ✔️ | -
| Create backend CRUD user | ✔️ | -
| Create view change password | ✔️ | -
| Create backend change password | ✔️ | -
| Backend restricting access | ✔️ | User can't access admin menu
2 | Add section user | - | On progress
| Design menu user | ✔️ | -
| Waiting meeting | ✔️ | -
| Requirements analysis | - | On progress
| Search and sort data | ✔️ | -
| Create view menu project | ✔️ | -
3 | Continue add section user | ✔️ | -
| Add section AME | ✔️ | -
| Restricting access | ✔️ | -
| Create view customers | ✔️ | -
| Design database relations | ✔️ | -
| Backend "project" | ✔️ | -
| Create view addproject | ✔️ | -
| Create backend addproject | ✔️ | -
4 | Create view task
Create backend task
Create event / timeline details
Create view details event
Create view task based event
Create backend details event
Create backend task based event
Create view main menu

## image
http://10.14.39.75:8080/project-management/
LOGIN PAGE
ADMIN PAGE
USER PAGE